## Table of Contents
TI Information - Selective Disclosure
Copyright (C) 2023 Texas Instruments Incorporated
Sheet No. | Title | Purpose
1 | Table of Contents | Provides an overview of the contents of the complete report.
2 | Script Input Parameters | Displays the input parameters provided to generate this report.
3 | Test Summary | Provides a summary report of Test Levels Vs Execution Statuses.
4 | Test Percentage Summary | Provides a summary report of Test Levels Vs Execution Statuses in percentages.
5 | Test Plan ¦ Execution Report | Provides the detailed report from Test Runs->Test Scenarios->Test Cases->Associated Issue(s) & Defects for the Test Run for which this report has been generated.
6 | Template Help | Provides Test Plan Template Guidelines/ Help.
7 | Revision History | Provides Template Revision History.

## Script Input Parameters
Test Run Key(s) | Report generated on
SITSW-2719 | 2023-07-10 05:39:05.908869-05:00 CDT

## Test Summary
Test Level ¦ Overall Status | Not Executed | Pass | Fail | Work In Progress | Blocked | Total Test Cases
Unit | 0 | 107 | 1 | 0 | 0 | 108
Integration | 0 | 0 | 0 | 0 | 0 | 0
Qualification | 0 | 0 | 0 | 0 | 0 | 0
Validation | 0 | 0 | 0 | 0 | 0 | 0
System | 0 | 0 | 0 | 0 | 0 | 0
Not Provided | 0 | 0 | 0 | 0 | 0 | 0
Overall Execution Results | 0 | 107 | 1 | 0 | 0 | 108

## Test Percentage Summary
Test Level ¦ Overall Status | Not Executed | Pass | Fail | Work In Progress | Blocked | Total Test Cases
Unit | 0% | 99% | 1% | 0% | 0% | 100%
Integration | 0% | 0% | 0% | 0% | 0% | 0%
Qualification | 0% | 0% | 0% | 0% | 0% | 0%
Validation | 0% | 0% | 0% | 0% | 0% | 0%
System | 0% | 0% | 0% | 0% | 0% | 0%
Not Provided | 0% | 0% | 0% | 0% | 0% | 0%
Overall Execution Results | 0% | 99% | 1% | 0% | 0% | 100%

## Test Plan ¦ Execution Report
Test Plan Key | Test Plan Name | Test Case Key | Test Case Name | Associated Issue(s) Type | Associated Issue(s) ID(s) | Test Platform | Test Level | Test Description | Test Setup | Pass/Fail Criteria | Test Type | Test Design Techniques | Test Execution Type | Test Category | Test Component(s) | Build/Release Key | Build/Release Name | Defect Key | Defect Summary | Overall Status
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2715 | IPC Notify: R5FSS0-0 to MCU-R5FSS0-0 | Requirement | SITSW-2445 | am62a-sk,am62p-sk | Unit | In this test, one CPU sends IPC notify to one other CPU. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos_nortos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2714 | IPC RPMSG: R5FSS0-0 to MCU-R5FSS0-0 with msgsize of 4 bytes | Requirement | SITSW-2445 | am62a-sk,am62p-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 4 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2713 | IPC RPMSG: R5FSS0-0 to MCU-R5FSS0-0 with msgsize of 32 bytes | Requirement | SITSW-2445 | am62a-sk,am62p-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 32 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2712 | IPC RPMSG: R5FSS0-0 to MCU-R5FSS0-0 with msgsize of 64 bytes | Requirement | SITSW-2445 | am62a-sk,am62p-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 64 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2711 | IPC RPMSG: R5FSS0-0 to MCU-R5FSS0-0 with msgsize of 112 bytes | Requirement | SITSW-2445 | am62a-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 112 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2710 | IPC Notify: Back to back messages to A53SS0-0 | Requirement | SITSW-2445 | am62a-sk | Unit | In this test, one CPU sends IPC notify without waiting for the other CPU to respond. If HW fifo is full it blocks to make sure no notify is missed and no errors in sending | <core_os:system_freertos_nortos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2703 | Mcasp audio playback test | Requirement,Requirement | SITSW-2735,SITSW-2736 | am62a-sk | Unit | Audio playback from Rx-to-Tx of MCASP1 using the onboard codec in the evm | <core_os:> | Audio from the microphone will be heard back on the speakers connected to the evm | Functional | Requirements-Analysis | Manual | Full | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2702 | Mcasp internal loopback test | Requirement,Requirement | SITSW-2735,SITSW-2736 | am62a-sk | Unit | Data loop back from Tx to Rx of McASP in internal loopback mode | <core_os:> | data transmitted and received should match. The test case will compare and print "All tests have passed" anything else like data mismatch or hang is a failure. | Functional | Requirements-Analysis | Manual | Full | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2690 | Linux Crash test |  |  | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Crash Linux and check if DM is running. | None | None | Functional | Requirements-Analysis | Manual | Full | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2677 | DM Firmware log test on SBL flow |  | No Associated Issues provided for the Test Case in Jira. | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Test the DM firmware log by enabling in the board configuration. | None | None | Functional | Requirements-Analysis | Manual | Full | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run | SITSW-2737 | DM log is not coming after boot. Only present during boot. | Fail
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2650 | Run vx_app_conformance_core.out | Requirement,Requirement,Requirement | SITSW-861,SITSW-1509,SITSW-1511 | am62a-sk | Unit | Run OpenVX conformance Test Refer UG for the steps to build and run the test Test setup: https://software-dl.ti.com/jacinto7/esd/processor-sdk-rtos-jacinto7/latest/exports/docs/vision_apps/docs/user_guide/BUILD_AND_RUN.html | ##UNIQUE_BUILD_STEPS##NONE ##COPY_FILES##NONE ##POST_TEST_STEPS##NONE ##MAIN_CORE##A72 ##DEPENDENT_FILE_PATHS##{vision_apps_out_dir}/{platform}/{main_core}/{os}/{release_type}/libtivision_apps.so,{vision_apps_out_dir}/{platform}/{main_core}/{os}/{release_type}/vx_app_heap_stats.out | It should run successfully and output should match with reference data | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2516 | Test SBL with C7x and DM R5 firmware from vision apps |  | No Associated Issues provided for the Test Case in Jira. | am62a-sk | Unit | Test SBL with C7x and DM R5 firmware from vision apps | None | None | Functional | Requirements-Analysis | Manual | Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2469 | IPC Notify: Any to any | Requirement,Requirement | SITSW-2504,SITSW-2434 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, each CPU notifies each other CPU via IPC notify | <core_os:system_freertos_nortos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2463 | IPC RPMSG: Any to Any | Requirement,Requirement | SITSW-2445,SITSW-2504 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, each CPU sends messages to each other CPU | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2458 | IPC RPMSG: Control endpoint point | Requirement,Requirement | SITSW-2443,SITSW-2445 | am62xx-sk,am62xx-sk-lp,am62a-sk,am62p-sk | Unit | In this test, we wait for a message announced on a control end point | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2457 | IPC Notify: Error handling | Requirement,Requirement | SITSW-2448,SITSW-2504 | am62xx-sk,am62xx-sk-lp,am62a-sk,am62p-sk | Unit | In this test, we test various error scenarios including wrong parameters, hw queue full condition, timeout tests | <core_os:system_freertos_nortos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2456 | IPC RPMSG: Error handling | Requirement | SITSW-2449 | am62xx-sk,am62xx-sk-lp,am62a-sk,am62p-sk | Unit | In this test, we test various error scenarios including wrong parameters, sw queue full condition, timeout tests, dropped messages | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2393 | DDR Inline ECC Test - MCU ESM | Requirement,Requirement | SITSW-2278,SITSW-2272 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | DDR Inline ECC tests handling ESM errors using MCU ESM in M4F | <core_os:system_nortos> | The application prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2340 | Serial NAND 1S mode test |  | No Associated Issues provided for the Test Case in Jira. | am62xx-sk-lp,am62a-sk | Unit | None | None | None |  |  | Manual |  | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-1940 | IPC Notify Sample Application | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-2436,SITSW-2435,SITSW-2440,SITSW-2438,SITSW-2504,SITSW-2439,SITSW-2437,SITSW-1798,SITSW-2434 | am62xx-sk,am62xx-sk-lp,am62a-sk,am62p-sk | Unit | The application tests the IPC notify feature across all cores. The main core sends notify message to all cores and waits for an ack from the remote cores | <core_os:system_freertos_nortos> | The main core prints "All pass" after receiving an ack from all remote cores. The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-1889 | IPC RpMsg Sample Application | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-2445,SITSW-2442,SITSW-2455,SITSW-2451,SITSW-2450,SITSW-2446,SITSW-1238,SITSW-2447,SITSW-2454,SITSW-2452,SITSW-2453,SITSW-2444,SITSW-2441,SITSW-1797 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application tests the IPC RpMsg feature across all cores. The main core sends RpMsg message to all cores and waits for an ack from the remote cores | <core_os:system_freertos_nortos> | The main core prints "All pass" after receiving an ack from all remote cores. The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-1632 | Bootloader: SBL OSPI NOR Linux | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1396,SITSW-1489,SITSW-1280,SITSW-1493,SITSW-1236,SITSW-1499,SITSW-1748,SITSW-1204,SITSW-742,SITSW-1473,SITSW-1846,SITSW-1701,SITSW-1041,SITSW-743 | am62xx-sk,am62a-sk | Unit | The application does a basic SOC initialization including loading SYSFW and boardcfg and will load and run multicore appimage of an application flashed at a particular offset in the OSPI Flash to the R5 and M4 cores and boots Linux on A53. | <core_os:r5fss0-0_nortos> <scripts:mpu_sbl_automation.py> <params_dut:bootmode="emmc";projectid="sbl_emmc_linux";test_setup="{ "bootmode": "emmc", "scripts": "mpu_sbl_automation.py", "hw_assets": "something", "core_os": ":r5fss0-0_nortos", "core": "r5fss0-0", "os": "_nortos", "am62ax-sk-lp-hsfs": { "uart_input": [ { "constraint": "am62axx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62axx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r0" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r8" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" } ] }, "am62x-sk-lp-hsfs": { "uart_input": [ { "constraint": "am62xx-lp-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-lp-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] }, "am62x-sk-hsfs": { "uart_input": [ { "constraint": "am62xx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] } }"> | The application boots Linux on A53 core and RTOS application on R5, M4 cores. Verify the boot by IPC between Linux and other cores | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-1630 | Bootloader: Null bootloader | Requirement,Requirement,Requirement,Requirement | SITSW-1477,SITSW-1476,SITSW-1236,SITSW-743 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application does basic SOC initialization including loading SYSFW and boardcfg and puts all the cores in WFI. Now application can be loaded from CCS by simply connecting to any core | <core_os:r5fss0-0_nortos><params_dut:projectid="hello_world";constraints="All\sdone";variables=bootmode:null><scripts:sbl_flash.py> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-1361 | IPC RpMsg Linux Sample Application | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1213,SITSW-2450,SITSW-2444,SITSW-2455,SITSW-2451,SITSW-1504,SITSW-2446,SITSW-2445,SITSW-2453,SITSW-739,SITSW-1241,SITSW-740,SITSW-2454,SITSW-2452,SITSW-2442,SITSW-2441,SITSW-1571 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This example shows message exchange bewteen Linux and RTOS/NORTOS cores. This example also does message exchange between the RTOS/NORTOS cores themselves. The Linux core initiates IPC with other core's by sending it a message. The other cores echo the same message to the Linux core. At the same time all RTOS/NORTOS cores, also send messages to each others and reply back to each other. i.e all CPUs send and recevive messages from each other | <core_os:system_freertos> | The main core prints "All pass" after receiving an ack from all remote cores. The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-1274 | DPL: Hwi nested | Requirement | SITSW-2431 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we post a HW interrupt and within this interrupt ISR we post another HW interrupt at higher priority. Variable to indicate ISR execution are checked to make sure the interrupt executed in required order | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Semi-Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2464 | IPC RPMSG: R5FSS0-0 to A53FSS0-0 with msgsize of 32 bytes | Requirement | SITSW-2445 | am62a-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 32 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2734 | IPC RPMSG: R5FSS0-0 to A53FSS0-0 with msgsize of 112 bytes | Requirement | SITSW-2445 | am62a-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 112 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2733 | IPC RPMSG: R5FSS0-0 to A53FSS0-0 with msgsize of 4 bytes | Requirement | SITSW-2445 | am62a-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 4 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2293 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Manual | SITSW-2732 | IPC RPMSG: R5FSS0-0 to A53SS0-0 with msgsize of 64 bytes | Requirement | SITSW-2445 | am62a-sk | Unit | In this test, one CPU sends messages to one other CPU with payload size of 64 bytes. This is a performance test, however performance results are only logged and not used to assert test pass or fail | <core_os:system_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Manual | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-2224 | BCDMA Interrupt Mode Memcpy Sample Application | Requirement | SITSW-1913 | am62xx-sk,am62a-sk | Unit | UDMA memcpy sample application performing block copy using Type 15 Transfer Record (TR15) using Transfer Record Packet Descriptor (TRPD) using BCDMA in interrupt mode | <core_os:r5fss0-0_freertos,a53ss0-0_nortos> | The application checks the destination buffer with the source buffer and prints pass on successful completion. Anything else like error prints, application hang is a failure | Functional | Requirements-Analysis | Automated | Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-2223 | DMA SW Trigger Sample Application | Requirement,Requirement,Requirement | SITSW-1913,SITSW-1058,SITSW-2503 | am62xx-sk,am62a-sk,am62p-sk | Unit | UDMA SW trigger sample application performs 3D transfer using SW trigger method. Each loop transfers M (icnt0 x icnt1) bytes of data MSMC size is M x N and Intermediate buffer size is just M bytes. Intermediate buffer memory set to wrap around after M bytes of transfer. Where M is icnt0 x icnt1 (UDMA_TEST_1D_SIZE x UDMA_TEST_2D_SIZE) and N is icnt2 = UDMA_TEST_3D_SIZE | <core_os:r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:a53ss0-0_nortos> | The application checks the destination buffer with the source buffer and prints pass on successful completion. Anything else like error prints, application hang is a failure | Functional | Requirements-Analysis | Automated | Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-2222 | DMA Chaining Sample Application | Requirement,Requirement,Requirement | SITSW-1913,SITSW-1058,SITSW-2503 | am62xx-sk,am62a-sk,am62p-sk | Unit | UDMA chaining sample application performing a chain of block copy using channel global trigger: CH0 -> CH1. The first channel doesn't user a global trigger and each channel triggers the next channel's global trigger through the channel's TR event register.A channel's source buffer is previous channel destination buffer. This ensures that chaining trigger worked in a synchronized manner when the memory compare matches | <core_os:r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:a53ss0-0_nortos> | The application checks the destination buffer with the source buffer and prints pass on successful completion. Anything else like error prints, application hang is a failure | Functional | Requirements-Analysis | Automated | Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-2174 | MMCSD: Raw Write/Read example for eMMC | Requirement,Requirement,Requirement | SITSW-2386,SITSW-756,SITSW-2385 | am62xx-sk,am62a-sk | Unit | The application demonstrates RAW I/O with the connected eMMC device. Known data is written to a certain offset in eMMC. This is then read back into a buffer and compared. | <core_os:r5fss0-0_freertos> | The application compares the written data and fails the test in case of mismatch. The application also checks all the return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail. | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-2103 | BCDMA Polled Mode Memcpy Sample Application | Requirement | SITSW-1913 | am62xx-sk,am62a-sk | Unit | UDMA memcpy sample application performing block copy using Type 15 Transfer Record (TR15) using Transfer Record Packet Descriptor (TRPD) using BCDMA in polled mode | <core_os:r5fss0-0_freertos,a53ss0-0_nortos> | The application checks the destination buffer with the source buffer and prints pass on successful completion. Anything else like error prints, application hang is a failure | Functional | Requirements-Analysis | Automated | Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-2096 | Test GTC counter | Requirement | SITSW-1491 | am62a-sk | Unit | Get the GTC counter with 1s interval and check if the value matches the GTC clock. | <core_os:mcu-r5fss0-0_nortos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Performance | Use Case Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-2092 | I2C LED Blink Sample Application | Requirement,Requirement,Requirement | SITSW-1773,SITSW-2502,SITSW-1913 | am62xx-sk,am62a-sk | Unit | The application controls and blinks the LED present in the EVM using I2C | <core_os:r5fss0-0_freertos,m4fss0-0_freertos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The application will blink all the I2C controlled LED in the EVM for 10 iterations. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1758 | Bootloader: UART Linux SBL | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1493,SITSW-1748,SITSW-745,SITSW-742,SITSW-1502,SITSW-1237,SITSW-733,SITSW-1812,SITSW-1473,SITSW-743 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application does basic SOC initialization including loading SYSFW and boardcfg and will look for a multicore appimage of an application flashed at a particular offset in the OSPI Flash and run it. It also boots Linux on A53 | <core_os:r5fss0-0_nortos> <scripts:mpu_sbl_automation.py> <params_dut:projectid="sbl_uart_linux";bootmode="uart";test_setup="{ "bootmode": "uart", "scripts": "mpu_sbl_automation.py", "hw_assets": "sbl", "core_os": ":r5fss0-0_nortos", "core": "r5fss0-0", "os": "_nortos", "am62ax-sk-hsfs": { "uart_input": [{ "constraint": "am62axx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62axx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r0" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r8" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" } ] }, "am62x-sk-lp-hsfs": { "uart_input": [{ "constraint": "am62xx-lp-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-lp-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] }, "am62x-sk-hsfs": { "uart_input": [{ "constraint": "am62xx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] } }"> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1757 | Bootloader: SBL OSPI NAND Linux | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-730,SITSW-1396,SITSW-743,SITSW-1476,SITSW-1236,SITSW-1473,SITSW-738,SITSW-742,SITSW-744,SITSW-1748,SITSW-2243,SITSW-1289,SITSW-1284,SITSW-1497,SITSW-1493,SITSW-1701,SITSW-1041 | am62xx-sk-lp,am62a-sk | Unit | The application does a basic SOC initialization including loading SYSFW and boardcfg and will load and run multicore appimage of an application flashed at a particular offset in the OSPI Flash to the R5 and M4 cores and boots Linux on A53. | <core_os:r5fss0-0_nortos> <core:r5fss0-0> <scripts:mpu_sbl_automation.py> <params_dut:bootmode="ospi_nand";projectid="sbl_ospi_nand_linux";variables="bootmode:ospi_nand";test_setup="{ "bootmode": "ospi_nand", "scripts": "mpu_sbl_automation.py", "hw_assets": "sbl", "core_os": ":r5fss0-0_nortos", "core": "r5fss0-0", "os": "_nortos", "am62ax-sk-hsfs": { "uart_input": [{ "constraint": "am62axx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62axx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r0" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r8" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" } ] }, "am62x-sk-lp-hsfs": { "uart_input": [{ "constraint": "am62xx-lp-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-lp-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] }, "am62xx-sk-hsfs": { "uart_input": [{ "constraint": "am62xx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] } }"> | The application boots Linux on A53 core and RTOS application on R5, M4 cores. Verify the boot by IPC between Linux and other cores | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1755 | Bootloader: SBL EMMC Linux | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1396,SITSW-730,SITSW-755,SITSW-1236,SITSW-2384,SITSW-743,SITSW-756,SITSW-1748,SITSW-742,SITSW-1473,SITSW-1493,SITSW-1701,SITSW-1287 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application does a basic SOC initialization including loading SYSFW and boardcfg and will load and run multicore appimage of an application flashed at a particular offset in the EMMC to the R5, M4 cores and boots Linux on A53. Confirm the EMMC init time is less than 100ms | <core_os:r5fss0-0_nortos> <scripts:mpu_sbl_automation.py> <params_dut:bootmode="emmc";projectid="sbl_emmc_linux";test_setup="{ "bootmode": "emmc", "scripts": "mpu_sbl_automation.py", "hw_assets": "sbl", "core_os": ":r5fss0-0_nortos", "core": "r5fss0-0", "os": "_nortos", "am62ax-sk-hsfs": { "uart_input": [ { "constraint": "am62axx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62axx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r0" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r8" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" } ] }, "am62x-sk-lp-hsfs": { "uart_input": [ { "constraint": "am62xx-lp-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-lp-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] }, "am62xx-sk-hsfs": { "uart_input": [ { "constraint": "am62xx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] } }"> | The application boots Linux on A53 core and RTOS application on R5, M4 cores. Verify the boot by IPC between Linux and other cores | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1634 | Bootloader: UART bootloader | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-2495,SITSW-1812,SITSW-745,SITSW-742,SITSW-1237,SITSW-1236,SITSW-733,SITSW-1502,SITSW-743 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application does basic SOC initialization including loading SYSFW and boardcfg and will look for a multicore appimage of an application flashed at a particular offset in the OSPI Flash and run it | <core_os:r5fss0-0_nortos> <scripts:mpu_sbl_automation.py> <params_dut:projectid="sbl_uart";constraints="";bootmode="uart";disable_a53_check="True";test_setup="{ "bootmode": "uart", "scripts": "mpu_sbl_automation.py", "hw_assets": "sbl", "core_os": ":r5fss0-0_nortos", "core": "r5fss0-0", "os": "_nortos", "am62ax-sk-hsfs": { "uart_input": [{ "constraint": "am62axx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62axx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r0" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r8" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" } ] }, "am62x-sk-lp-hsfs": { "uart_input": [{ "constraint": "am62xx-lp-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-lp-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] }, "am62x-sk-hsfs": { "uart_input": [{ "constraint": "am62xx-evm login:", "timeout": 300, "message": "Linux Login Prompt appeared", "depends_prev": "False", "port": "mpu", "send_command_with_newline": "1", "command": "" }, { "constraint": "root@am62xx-evm", "timeout": 30, "message": "root login successful", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "root" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r15" }, { "constraint": "TEST STATUS: PASSED", "timeout": 30, "message": "rpmsg command verified", "depends_prev": "True", "port": "mpu", "send_command_with_newline": "1", "command": "rpmsg_char_simple -r9" } ] } }"> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1463 | FreeRTOS Posix Demo Application | Requirement,Requirement,Requirement,Requirement | SITSW-2508,SITSW-728,SITSW-860,SITSW-1475 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates the posix demo which is available as part of FreeRTOS Posix repo | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,a53ss0-0_freertos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1462 | Hello world cpp application | Requirement | SITSW-1212 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Simplified hello world example built with the cpp compiler options | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos><params_dut:projectid="hello_world_cpp";constraints="Hello\sWorld"> | The application prints 'Hello World' on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1461 | FreeRTOS Task Switch Application | Requirement,Requirement,Requirement,Requirement | SITSW-1475,SITSW-2398,SITSW-728,SITSW-860 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates the task switching with FreeRTOS. The application creates two tasks and shows how to switch between the task by using periodic timer and posting the task semaphores. It also prints the task switching time. | <core_os:m4fss0-0_freertos><core_am62ax-sk-lp-hsfs:r5fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Performance | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1457 | FreeRTOS: test stdatomics.h | Requirement,Requirement,Requirement | SITSW-728,SITSW-1475,SITSW-860 | am62a-sk | Unit | This test will check operation from stdatomics.h This checks atomic increments between the current task and ISR. And then checks atomic increments between multiple tasks as well as ISR For the task to switch asychronoulsy, we should ideally make configUSE_TIME_SLICING as 1, since will cause a task switch while the variable is being incremented However even if not 1, the test will still pass. | <core_os:mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Customer Usage | Automated | Regression,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1455 | DPL: Queue | Requirement,Requirement,Requirement,Requirement | SITSW-2508,SITSW-2408,SITSW-2406,SITSW-2407 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test we create a queue and put the elements in it and get the elements back from queue and check they come in same order. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1437 | McSPI Low Latency Sample Application 8bit | Requirement,Requirement,Requirement | SITSW-735,SITSW-1221,SITSW-1913 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates McSPI driver low latency API operations and measure the transfer duration of 8bit data width | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Performance | Use Case Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1436 | McSPI Low Latency Sample Application 32bit | Requirement,Requirement,Requirement | SITSW-1221,SITSW-735,SITSW-1913 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates McSPI driver low latency API operations and measure the transfer duration of 32bit data width | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Performance | Use Case Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1435 | McSPI Internal Loopback Sample Application | Requirement,Requirement,Requirement | SITSW-735,SITSW-1221,SITSW-1913 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates McSPI RX and TX operation by sending a known data and then receiving the same in RX mode by enabling internal pad level loopback | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos> | The application compares the received data with TX data and fails the test incase of mismatch. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1351 | GPIO Macro Test | Requirement,Requirement,Requirement | SITSW-1219,SITSW-2500,SITSW-730 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The test performs various conversion macros | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The test checks if the expected value is returned by macros. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Generation and Analysis of Equivalence Classes | Automated | Full,Regression | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1350 | GPIO Trigger Test | Requirement,Requirement,Requirement,Requirement | SITSW-1219,SITSW-2500,SITSW-731,SITSW-730 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The test performs various trigger test by configuring the GPIO as output and checks if the trigger is causing the interrupt status to get set | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The test checks if the expected trigger count is reached. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Regression | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1349 | GPIO Read Test | Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1219,SITSW-731,SITSW-2500,SITSW-1285,SITSW-730 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The test performs pin read API and prints the value on console | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The GPIO value should get printed on console. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Regression | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1348 | GPIO Output Test | Requirement,Requirement,Requirement,Requirement | SITSW-1219,SITSW-2500,SITSW-730,SITSW-731 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The test performs output API and read back the output register and verify it is same as what is set | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The LED should blink for a specified duration. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Regression | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1320 | I2C EEPROM Read Write Test, Polling Mode, 400KHZ | Requirement,Requirement,Requirement | SITSW-1222,SITSW-732,SITSW-2502 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the I2C Write/Read functionality by writing a byte at the end of the EEPROM and reading it back in Polling Mode at 400KHZ frequency | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,.a53ss0-0_nortos> | The test checks if the byte read is equal to byte written. The application also checks all return value of all API and prints | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1319 | I2C Timeout Test | Requirement,Requirement,Requirement | SITSW-1222,SITSW-2502,SITSW-732 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the timeout functionality of the I2C Driver by writing to a non-existent peripheral | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | This test checks if the expected timeout occurs. The application also checks all return value of all API and prints | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1318 | I2C Open/Close Test | Requirement,Requirement,Requirement | SITSW-1222,SITSW-2502,SITSW-732 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This test demonstrates the open/close functionality of the driver in loop | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | This test checks if a value can be read after opening the driver in loop. The application also checks all return value of all API and prints | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1317 | I2C EEPROM Read Write Test, Callback Mode, 100KHZ | Requirement,Requirement,Requirement | SITSW-1222,SITSW-732,SITSW-2502 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the I2C Write/Read functionality by writing a byte at the end of the EEPROM and reading it back in Callback Mode at 100KHZ frequency | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The test checks if the byte read is equal to byte written. The application also checks all return value of all API and prints | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1316 | I2C0 Probe Test | Requirement,Requirement | SITSW-1222,SITSW-732 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrated the probing capability of the driver from I2C0 | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | This test checks if the addresses that result from the probe are same as in schematic. The application also checks all return value of all API and prints | Interface | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1315 | I2C Set Bus Frequency Test | Requirement,Requirement | SITSW-1222,SITSW-2502 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This test demonstrates the I2C Driver's functionality to change bus frequency by writing and reading after changing the frequency | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | This test checks if the byte read is equal to the byte written after a frequency change | Interface | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1314 | I2C EEPROM Read Write Performance Test, Blocking, 400KHZ | Requirement,Requirement,Requirement | SITSW-1222,SITSW-2502,SITSW-732 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the I2C's functionality to write and read byte 10 times at end of EEPROM in Blocking Mode at 400KHZ frequency | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The test checks if the bytes read are equal to bytes written. The application also checks all return value of all API and prints | Performance | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1313 | I2C EEPROM Multiple Bytes Read Write Test, Blocking, 400KHZ | Requirement,Requirement,Requirement | SITSW-1222,SITSW-2502,SITSW-732 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the I2C's functionality to write and read multiple bytes at end of EEPROM in Blocking Mode at 400KHZ frequency | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The test checks if the bytes read are equal to bytes written. The application also checks all return value of all API and prints | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1312 | I2C EEPROM Read Write Test, Blocking, 100KHZ | Requirement,Requirement | SITSW-1222,SITSW-732 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the I2C Write/Read functionality by writing a byte at the end of the EEPROM and reading it back in Blocking Mode at 100KHZ frequency | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The test checks if the byte read is equal to byte written. The application also checks all return value of all API and prints | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1311 | I2C EEPROM Read Write Test, Blocking, 400KHZ | Requirement,Requirement,Requirement | SITSW-1222,SITSW-2502,SITSW-732 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the I2C Write/Read functionality by writing a byte at the end of the EEPROM and reading it back in Blocking Mode at 400KHZ frequency | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The test checks if the byte read is equal to byte written. The application also checks all return value of all API and prints | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1310 | I2C EEPROM Read Sample Application | Requirement,Requirement,Requirement,Requirement | SITSW-1222,SITSW-2502,SITSW-732,SITSW-730 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application reads data from the EEPROM in the EVM using I2C | <core_os:m4fss0-0_nortos,r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1309 | UART Low Latency Sample Application Polling | Requirement,Requirement,Requirement | SITSW-1217,SITSW-733,SITSW-2505 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This example demonstrate the UART low latency API in polling mode. The application echo the received char and when user types 8 characters, the application ends | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> <params_dut:projectid="uart_echo_low_latency_polling";commands=tout:60,exp:"back and exits","12345678\\r\\n",exp:"12345678"> | The application checks if RX buffer has any data and reads the data from it and copy it to TX buffer and initiate the UART TX (echo). The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Customer Usage | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1308 | UART Low Latency Sample Application Interrupt | Requirement,Requirement,Requirement,Requirement | SITSW-1217,SITSW-733,SITSW-2505,SITSW-730 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This example demonstrate the UART low latency API and user managed interrupt service routine. The application echo the received char and when user types 8 characters, the application ends | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> <params_dut:projectid="uart_echo_low_latency_interrupt";commands=tout:60,exp:"back and exits","12345678\\r\\n",exp:"12345678"> | The application checks if RX buffer has any data and reads the data from it and copy it to TX buffer and initiate the UART TX (echo). The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Customer Usage | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1307 | UART Echo Non-Blocking Sample Application | Requirement,Requirement,Requirement | SITSW-1217,SITSW-733,SITSW-2505 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates UART RX and TX operation by echoing char that it receives in non-blocking mode of operation. When user types 8 characters, the application ends | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos,a53ss0-0_nortos> <params_dut:projectid="uart_echo_callback";commands=tout:60,exp:"Please input","12345678\\r\\n",exp:"12345678"> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1306 | UART Echo Sample Application | Requirement,Requirement,Requirement | SITSW-1217,SITSW-2505,SITSW-733 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates UART RX and TX operation by echoing char that it receives. When user types quit, the application ends | <core_os:m4fss0-0_nortos,r5fss0-0_freertos><core_am62xx-sk-lp-hsfs:m4fss0-0_nortos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos,a53ss0-0_nortos><params_dut:projectid="uart_echo";commands=tout:60,exp:"Please input","87654321\\r\\n",exp:"87654321"> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1305 | UART0_RX_TO_TX_Interrupt_115200Baudrate_Default_ReadMode_Partial Test | Requirement,Requirement,Requirement | SITSW-1217,SITSW-2505,SITSW-733 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the UART Read/Write functionality by Sending 1000 bytes through UART console and see the same echoed back in console, Interrupt Mode, Read Mode PARTIAL | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos> | The application echos the received TX data and fails the test incase of error. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1304 | UART0_RX_TO_TX_Interrupt_115200Baudrate_Default | Requirement,Requirement,Requirement | SITSW-1217,SITSW-2505,SITSW-733 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the UART Read/Write functionality by Sending 1000 bytes through UART console and see the same echoed back in console, Interrupt Mode | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos> | The application echos the received TX data and fails the test incase of error. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1303 | UART0_TX_RX_Polled_115200Baudrate_Default | Requirement,Requirement,Requirement | SITSW-1217,SITSW-2505,SITSW-733 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the UART Write functionality by transmitting the configured number of bytes and UART Read functionality by reading them back in Polling Mode | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos> | The application checks if RX buffer has any data and reads the data from it and copy it to TX buffer and initiate the UART TX (echo). The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1302 | MCAN Internal Loopback Sample Application Polling Mode | Requirement,Requirement,Requirement | SITSW-1220,SITSW-734,SITSW-1913 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates MCAN RX and TX polling mode operation by sending a known message id and the data and then receiving the same in RX mode by enabling internal loopback and finally compare the results. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos> | The application compares the received data with TX data and fails the test incase of mismatch. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1300 | MCAN Internal Loopback Sample Application Interrupt Mode | Requirement,Requirement,Requirement | SITSW-1220,SITSW-1913,SITSW-734 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates MCAN RX and TX interrupt mode operation by sending a known message id and the data and then receiving the same in RX mode by enabling internal loopback and finally compare the results. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos> | The application compares the received data with TX data and fails the test incase of mismatch. The application also checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1298 | SCIClient: Get Version Test | Requirement,Requirement,Requirement,Requirement | SITSW-1216,SITSW-2506,SITSW-1359,SITSW-1876 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application demonstrates the "get version" functionality of SCIClient with which we can query the current version of SYSFW | <core_os:m4fss0-0_nortos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,r5fss0-0_freertos,a53ss0-0_nortos> | The application should print the correct version of the SYSFW on the console. Any thing else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1297 | SCIClient: Timeout Test | Requirement,Requirement,Requirement | SITSW-1216,SITSW-1359,SITSW-2506 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application checks if the Sciclient_service API fails given a particular timeout | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The application should print test pass. Any error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1296 | SCIClient: Invalid Param Test | Requirement,Requirement,Requirement | SITSW-1216,SITSW-2506,SITSW-1359 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This application checks if the Sciclient_service API fails if we provide an incorrect/NULL request or response parameter | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The application should print test pass. Any error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1294 | SCICLIENT Get Version Sample Application | Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1216,SITSW-2506,SITSW-1281,SITSW-1359,SITSW-1876 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application gets the DMSC firmware version and does a ABI check | <core_os:m4fss0-0_nortos,r5fss0-0_freertos><core_am62ax-sk-lp-hsfs:mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1279 | FreeRTOS: Test task and CPU load measurement | Requirement,Requirement,Requirement | SITSW-806,SITSW-1475,SITSW-860 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Test task and CPU load measurement APIs | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Regression | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1278 | DPL: SOC Address Conversion Function Tests | Requirement | SITSW-2419 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Test the physical to virtual and virtual to physical conversion functions for all the cores in the device. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1277 | DPL: Event | Requirement | SITSW-2398 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we test event create, destruct, get, set, clear and wait. We also test set, get, and clear from ISR context. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the function exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1276 | FreeRTOS event group test with ISRs | Requirement,Requirement | SITSW-1475,SITSW-860 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Test FreeRTOS event groups with "from ISR" APIs | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | test case pass in UT | Functional | Requirements-Analysis | Automated | Regression | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1275 | FreeRTOS event group test with tasks | Requirement,Requirement | SITSW-860,SITSW-1475 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Test FreeRTOS event groups with task switches | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | test case pass in UT | Functional | Requirements-Analysis | Automated | Regression | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1273 | DPL: Task | Requirement | SITSW-2398 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we create a task using TaskP and make sure we can switch between the new task and current task. TaskP_yield and Task_exit() is also tested | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1272 | DPL: Hwi profiling | Requirement,Requirement,Requirement,Requirement | SITSW-2430,SITSW-2431,SITSW-2432,SITSW-2429 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we measure Hwi interrupt response time with and without semaphore APIs. The timing info is logged and not assert checked for expected value | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1271 | DPL: Debug Log | Requirement,Requirement | SITSW-2409,SITSW-2508 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we test logging to different zones, enable/disable of zones, and logging to CCS and UART | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1270 | DPL: Cycle Counter | Requirement,Requirement,Requirement | SITSW-2508,SITSW-2433,SITSW-1218 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we test cycle counter by measuring time across 1ms, 10ms, 100ms, the cycle counter values should proportionately increase each time | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1269 | DPL: Heap | Requirement,Requirement,Requirement,Requirement | SITSW-2421,SITSW-2423,SITSW-2422,SITSW-2420 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we create a arbitrary heap and test alloc, free and heap size APIs | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1268 | DPL: Clock sleep | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1218,SITSW-2414,SITSW-2428,SITSW-2418,SITSW-2416,SITSW-2415,SITSW-2417 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we test sleep, usleep APIs and confirm the delay matches measured time | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1267 | DPL: Clock one-shot | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1218,SITSW-2424,SITSW-2412,SITSW-2411,SITSW-2416,SITSW-2508,SITSW-2399,SITSW-2428,SITSW-2417,SITSW-2413,SITSW-2410 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we start a SW timer in one-shot mode using CLockP API. We wait for one callback to post a semaphore. Time is measured to confirm the elapsed time. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1266 | DPL: Semaphore timeout | Requirement | SITSW-2404 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we test the timeout feature of semaphore, but pending on a semaphore than is not posted. The elapsed time is confirmed by measuring it using the ClockP API | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1265 | DPL: Semaphore Counting | Requirement,Requirement,Requirement,Requirement | SITSW-2405,SITSW-2402,SITSW-2508,SITSW-2404 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we create a counting semaphore, post a interrupt and within the ISR post the semaphore and wait on the semaphore in the task. This done in a loop thus testing the counting semaphore | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1264 | DPL: Semaphore Binary | Requirement,Requirement,Requirement,Requirement | SITSW-2405,SITSW-2404,SITSW-2508,SITSW-2401 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we create a binary semaphore, post a interrupt and within the ISR post the semaphore and wait on the semaphore in the task | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1263 | DPL: Semaphore Mutex | Requirement,Requirement,Requirement,Requirement | SITSW-2508,SITSW-2404,SITSW-2403,SITSW-2405 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we test mutex create, destruct, pend, post. We also test recursive taking of mutex within the same task and over multiple iterations | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1262 | DPL: Hwi | Requirement,Requirement,Requirement | SITSW-2429,SITSW-2508,SITSW-2431 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we post a HW interrupt and check if the ISR is called. We also check Hwi_inISR API to make sure it return the correct value in ISR and outside ISR | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1261 | FreeRTOS: Test Timer and interrupts in continuous mode | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1475,SITSW-2428,SITSW-2424,SITSW-2425,SITSW-2426,SITSW-860,SITSW-728 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test. A timer is programmed to tick every 10us, task a delay of 1s and the number of interrupt counted. | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1260 | FreeRTOS: Task delay | Requirement,Requirement | SITSW-860,SITSW-1475 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we call vTaskDelay to suspend task for a known duration, we measure time using ClockP APIs and check if elsaped time matches the delay | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1259 | FreeRTOS: Task switch with float operations | Requirement,Requirement,Requirement | SITSW-1475,SITSW-2398,SITSW-860 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, task A and task B switch each other using semaphore's and task performs floating point operations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1257 | FreeRTOS: Task to ISR using "task notify" and WITH task switch | Requirement,Requirement,Requirement,Requirement | SITSW-860,SITSW-2508,SITSW-2398,SITSW-1475 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, task A posts a interrupt and the interrupt posts a "task notify" which task B is waiting on. Task B then posts a "task notify" that task A is waiting on. This is run in a loop of multiple iterations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1256 | FreeRTOS: Task to ISR using semaphore and WITH task switch | Requirement,Requirement,Requirement,Requirement | SITSW-860,SITSW-2398,SITSW-728,SITSW-1475 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, task A posts a interrupt and the interrupt posts a semaphore which task B is waiting on. Task B then posts a semaphore that task A is waiting on. This is run in a loop of multiple iterations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1255 | FreeRTOS: Task to ISR using "task notify" and NO task switch | Requirement,Requirement,Requirement,Requirement | SITSW-860,SITSW-728,SITSW-2508,SITSW-1475 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, task A posts a interrupt and the interrupt posts a "task notify" which task A is waiting on it. This is run in a loop of multiple iterations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1254 | FreeRTOS: Task to ISR using semaphore and NO task switch | Requirement,Requirement,Requirement,Requirement | SITSW-1475,SITSW-2398,SITSW-728,SITSW-860 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, task A posts a interrupt and the interrupt posts a semaphore which task A is waiting on it. This is run in a loop of multiple iterations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1253 | FreeRTOS: Task yield | Requirement,Requirement,Requirement | SITSW-1475,SITSW-728,SITSW-860 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this tast, task A continuously post task Yield in a loop of multiple iterations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1252 | FreeRTOS: Task switch with "task notify" | Requirement,Requirement,Requirement,Requirement | SITSW-860,SITSW-1475,SITSW-2508,SITSW-728 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In the test two tasks are created, task A posts "task notify" to Task B who waits on it and then task B posts a "task notify" to task A who is waiting on it. This is run in a loop of multiple iterations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1251 | FreeRTOS: Task switch with semaphore | Requirement,Requirement,Requirement | SITSW-1475,SITSW-860,SITSW-2398 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In the test two tasks are created, task A posts semaphore to Task B who waits on it and then task B posts a semaphore to task A who is waiting on it. This is run in a loop of multiple iterations | <core_os:m4fss0-0_freertos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1250 | Hello world application | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-1215,SITSW-1211,SITSW-1212,SITSW-1240,SITSW-1223,SITSW-729,SITSW-2400,SITSW-2508,SITSW-1360,SITSW-1494 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | Simplified hello world example | <core_os:m4fss0-0_freertos,m4fss0-0_nortos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_freertos,a53ss0-0_nortos><params_dut:projectid="hello_world";constraints="Hello\sWorld"> | The application prints 'Hello World' on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1249 | DPL demo Sample Application | Requirement,Requirement,Requirement | SITSW-2432,SITSW-2508,SITSW-2398 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | The application demonstrates the various module features of DPL: HWI, Clock, Cache, Heap | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos,r5fss0-0_freertos,a53ss0-0_freertos, a53ss0-0_nortos> | The application checks all return value of all API and prints pass on successful completion. Anything else like error prints or test hang is a fail | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1247 | Empty FreeRTOS Sample Application | Requirement,Requirement,Requirement | SITSW-2508,SITSW-860,SITSW-1475 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This is an empty application that prints "All Pass" and ends. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_nortos,mcu-r5fss0-0_freertos> | The main core prints "All pass" and the application ends after this | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1246 | Empty No RTOS Sample Application | Requirement,Requirement | SITSW-2508,SITSW-1223 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | This is an empty application that prints "All Pass" and ends. | <core_os:m4fss0-0_nortos,mcu-r5fss0-0_nortos,a53ss0-0_nortos> | The main core prints "All pass" and the application ends after this | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass
SITSW-2717 | MCU PLUS SDK AM62A v09.00.00 Test Plan - Automated | SITSW-1235 | DPL: Clock continuous | Requirement,Requirement,Requirement,Requirement,Requirement,Requirement | SITSW-2411,SITSW-2410,SITSW-2508,SITSW-2416,SITSW-2413,SITSW-1218 | am62xx-sk,am62xx-sk-lp,am62a-sk | Unit | In this test, we start a SW timer in continuous mode using CLockP API. We wait for multiple callbacks. Time is measured to confirm the elapsed time. | <core_os:m4fss0-0_nortos,m4fss0-0_freertos,r5fss0-0_freertos,mcu-r5fss0-0_freertos,mcu-r5fss0-0_nortos,a53ss0-0_nortos,a53ss0-0_freertos> | No hang, the loop exits successfully. All unity test framework asserts are successful | Functional | Requirements-Analysis | Automated | Full,Sanity | MCU+SDK | SITSW-2719 | MCU PLUS SDK AM62A v09.00.00 Test Run |  |  | Pass

## Template Help
Report | Test Matrix Field | Description | QRAS AP00216 Baseline Process | QRAS AP00216 Automotive and Functional Safety
Test Plan | Test Plan Key | Unique Test Plan Key (Map Test Scenario from QMetry) | Required | Required
| Test Plan Name | Test Plan Summary (Map Test Scenario from QMetry) | Required | Required
| Test Case Key | Unique Test Case Key | Required | Required
| Test Case Name | Test Case Summary | Required | Required
| Associated Issue(s) Type | **For BQ projects, typically SPS ID's (Requirements) are mapped. **For Automotive(AQ) Functional Safety (FSQ) projects ->This field provides the tracebility mapping for derived Test cases. This field shows whether its "Requirement, Architecture or Design". Ideal Mapping: Qualification Tests <->Requirement Integration Tests <-> Architecture Unit Tests <-> Design | Required | Required
| Associated Issue(s) ID(s) | Provides the Issue ID | Required | Required
| Test Platform | This field specifies the test results. There should be a separate column for each supported platform (e.g., Platform A, Platform B, Platform C, …) and a overall test result based on the test result for each platform. | Required | Required
| Test Level | (Map Test Scope from Qmetry) -- "Unit" for Software Unit Test -- "Integration" for Software Integration Test -- "System" for System Test -- "Qualification" for Software Qualification Test (aka Software Acceptance Test) -- "Validation" for Validation Test -- "Not Provided" if no 'Test Scope' is provided in Jira | Optional | Required
| Test Description | Detailed description of the test and steps required | Required | Required
| Test Setup | Reference to the required test hardware set-up and environment | Required | Required
| Pass/Fail Criteria | A description of the pass and fail criteria for the test case (Map Success Criteria from Qmetry) | Required | Required
| Test Type | The test plan is expected to leverage various types of testing to demonstrate software meets expectations. This field identifies the type of test associated with the test case. The types of tests are described below: (Map Test Method from Qmetry) | Optional | Required
|  | Functional: Tests covering functional requirements-based aspects of the software | Optional | Required
|  | Compatability: Test Case covers compatability with other systems in the environment. ISO/IEC/IEEE 29119-1 Defn: type of testing that measures the degree to which a test item can function satisfactorily alongside other independent products in a shared environment (co-existence), and where necessary, exchanges information with other systems or components (interoperability) | Optional | Required
|  | Usability: Test Case covers usability/api/look and feel aspects of the module including out-of box (OOB) experience | Optional | Required
|  | Fault Injection: Testing based on injection of errors or faults to ensure no unintended consequences | Optional | Required
|  | Performance: Test Case covers performance, profiling, latency etc. ISO/IEC/IEEE 29119-1 Defn: type of testing conducted to evaluate the degree to which a test item accomplishes its designated functions within given constraints of time and other resources | Optional | Required
|  | Reliability: Test Case ensures that the component does not fail over time ISO/IEC/IEEE 29119-1 Defn: type of testing conducted to evaluate the ability of a test item to perform its required functions, including evaluating the frequency with which failures occur, when it is used under stated conditions for a specified period of time | Optional | Required
|  | Stress: Test Case checks for API stability, load/unload of modules, create/delete, stress under different load conditions etc. ISO/IEC/IEEE 29119-1 Defn: type of performance efficiency testing conducted to evaluate a test item's behaviour under conditions of loading above anticipated or specified capacity requirements, or of resource availability below minimum specified requirements | Optional | Required
|  | Security: Test Case covers security aspects such as authentication and authorization, use of crypographic protocols, proper confiugration firewalls, etc. ISO/IEC/IEEE 29119-1 Defn: type of testing conducted to evaluate the degree to which a test item, and associated data and information, are protected so that unauthorized persons or systems cannot use, read, or modify them, and authorized persons or systems are not denied access to them | Optional | Required
|  | Maintainability: Test Case covers the ease at which the system can be modified. Typically maintainability tests are static tests and/or code review/inspection driven. ISO/IEC/IEEE 29119-1 Defn: test type conducted to evaluate the degree of effectiveness and efficiency with which a test item may be modified | Optional | Required
|  | Portability: Test case covers the ease at which the system can moved to another environment. This includes installability testing. ISO/IEC/IEEE 29119-1 Defn: type of testing conducted to evaluate the ease with which a test item can be transferred from one hardware or software environment to another, including the level of modification needed for it to be executed in various types of environment | Optional | Required
| Test Design Technique | Tests are dervied using one or more Test Design Techniques. These techniques consist of "activities, concepts, processes, and patterns used to construct a test model that is used to identify test conditions for a test item, derive corresponding test coverage items, and subsequently derive or select test cases" (IEEE 29119-2:2013, definition 4.59) See ISO/IEC/IEEE 29119-4 for a complete list of common design techniqes and their definitions. Some of the techniques from 29119-4 include: Equivalence Partitioning, Boundary Value Analysis, Use case analysis; Customer Usage; Requirement analysis; Failure Mode analysis and Error Guessing. (Map Test Derivation Method from Qmetry) | Optional | Required
|  | Requirements-Analysis: Test cases derived to demonstrate intended functionality of the software derived from analysis of software requirements | Optional | Required
|  | Boundary Value Analysis: Test cases that apply to interfaces and values approaching and crossing the boundaries and out of range values | Optional | Required
|  | Error Guessing: Test cases established based on lessons learned and expert judgement to determine situations that may cause software failures or errors to appear | Optional | Required
|  | Other (Use case analysis; Customer Usage; Requirement analysis; Failure Mode analysis): Teams are encouraged to use techniques defined by standards such as ISO/IEC/IEEE 29119-4; which needs to be refelcted within Qmetry | Optional | Optional
| Test Execution Type | Identifies whether the case is automated or manually or Semi-Automated executed | Optional | Required
| Test Category | Test Categories represent sets of tests that are commonly used. | Optional | Required
|  | Sanity: This Test case is identified to run for Sanity Checks. These are mainly the basic tests that need to be run as part of entry to validate phase | Optional | Required
|  | Full: This category means running all test cases for identified releases | Optional | Required
|  | Base Regression: This Test case is identified to run for the Base Regression / maintenance releases | Optional | Required
| Test Component(s) | The field provides the Component(s) (in Jira) to which the Test Case is mapped to. | Optional | Optional
Test Execution | Build/Release Key | Software build name/information for which the test results apply. (Map Test Run Key issuetype from Qmetry) | Required | Required
| Defect Key | This field provides necessary JIRA Bug ID for any failed test cases. | Required | Required
| Defect Summary | This field provides necessary JIRA Bug Summary for any failed test cases. | Required | Required
| Overall Status | NOT EXECUTED Test Not Executed | Required | Required
|  | PASS Test Passed | Required | Required
|  | FAIL Test Failed | Required | Required
|  | BLOCKED Test Blocked because of other test case failure, an Open MR from previous Release, feature not implemented yet, feature not supported by hardware | Required | Required
|  | WIP Test is currently Work In Progress. | Required | Required

## Template Revision History
Author | Version | Date | Description
Frank Fruth | A | 31st Aug, 2018 | Initial version
Frank Fruth | B | 23rd Oct, 2018 | Clean-up. Removed some tabs that were erroneously left in by mistake.
Frank Fruth | C | 9th Nov, 2018 | Updates to align with FoQus import feature for EXCEL test reports/ Importing EXCEL test reports to FoQus allows leveraging of bi-directional report traceability and metrics. -- Added Overall Test Status column under test results -- Modified HELP - Test scope to align on specific values: Unit, Integration, Qualification. These are expected values used by FoQus. -- Added project level detail information to summary page (e.g., product name, version, report date, Platform, OS)
Frank Fruth | D | 4th Jun, 2019 | EPSWDEVCCB-80: - Removed Category Column on Test Details. This was a duplicate of Test Categories column. - Removed Test Adequacy Coumn on Test Details this was a duplicate of Test Methods Column - Replaced "IR" Column with "Defect(s)" as a more accurate column heading. - Added more description to test results on Help tab to explain Platforms and Overall Results
Erik Shreve | E | 8th Oct, 2019 | - EPSWDEVCCB-82: Aligned terms with ISO/IEC/IEEE 29919 - Removed "Test Area/Scope" as it is not part of individual test case/procedure specificaitons. - Removed "Full" test category as it is redundant. - Added "Test Set(s)" column to allow for custom test sets. - Added FMEA ID to column used for tracing. - Added additional Test Types. Removed Test Design Techniques not used for ISO 26262 compliance and added an "Other" column so teams can specify any other technique they use.
Gayathri Ajith | F | 21st July, 2022 | Modification of Test plan/Test Report Template to include below changes - Modified coloumns ->Test type; Test Design Technique; Test Category; Test Execution ;which helps to pick data from respective Test management tools - Removed "Test set" field as Test Plan will provide evidence for Test case selection (Test Senario) - Qmetry fields -Test Method and Test scope fields within Qmetry has been added with few parameters as identified under EPSWDEVCCB-437 - Summary page included with Test Scope summary - Help Page modified to include changes
Gayathri Ajith | G | 25th Oct, 2022 | Modified the template based on automation done EPSWDEVCCB-428 1. Added Table of Contents and Script Input Parameters sheet 2. Modified "Test summary" sheet to capture test summary details for all test levels; also modified "Test Plan ¦ Execution Report" sheet to include Test plan key ID and assoisated issue types and ID's 3. Updated Help page with changes done